## Some Hints and Explanations
some hints and explanations concerning this template
About this template:
This template is supposed to help you developing your project schedule.
On the "Milestones + Packages" Sheet you may input your milestones and subtasks with all necessary information (although you may add some columns, of course).
The very first column defines the type of this row: (M) defines Milestone, (S),(S1),(S2),(S3) subtasks (the number currently only defines its color in the gantt chart. A milestone should be of duration "1" (meaning it's a single date).
Also, you may enter the team members' names in Cells H2:L2, which should suffice in order to update the remaining sheets.
The "Time Sheets TM1" - "Time Sheet TM5" may be used to keep track of your workload. For each team member, mark the assigned tasks on the "Milestones + Packages" Sheet in columns H to L by inserting an "x". You can then choose those tasks in the first column "Task" in the respective table on the time sheet via a drop down menu. Be careful to find a way of updating your individual work loads that avoids file version conflicts of your .xlsx File.
You may use the "Gantt Chart" sheet for printing your schedule.
There is one unpleasant issue: Moving rows may cause Excel to adapt referenced formulas in the gantt chart. You may therefore prepare (and order) the schedule on a temporary sheet and then copy it into the main sheet. Also, you must take care to only copy values (no formattting) when doing so.
First steps:
We suggest the following steps:
1) Enter your team members names in the cells H2:L2 on "Milestones + Packages", you may delete the 5th one if not needed.
2) Switch to the "temporary" sheet to develope your schedule. Reason: You can change any row contents in "Milestones + Packages", but you will not be able to permute rows nor to insert new ones. Define your milestones and subtasks, arrange them in a reasonable order.
3) Copy the "temporary" cells to the "Milestons + Packages" sheet, but only by value (such that no format rules are overwritten). In order to do so, mark the respective cells, copy them, mark the first cell on the "Milestones + Packages" sheet, and select "Value (V)" in the context menu (or press "V").
4) You may adapt colors in the gantt chart by changing the A-column entry.
5) Print your gantt chart.
Of course, feel free to adapt and improve and correct this template. If you can come up with something particularly useful, it would be nice to let us know so that future case studies may benefit as well!

## Milestones + Packages
Milestones & Workpackages
Milestones & Workpackages
Typ | Name | Description | Result | Start | Duration (days) | Responsible | Annkathrin | Sabina | Christian | Johannes
(M) | Project Schedule | Develop a project schedule for the whole project. This contains all milestones and the corresponding subtasks in a SMART way. |  | 2015-04-22 | 1 | Team | x | x | x | x
(S) | Define Milestones & Packages | Define the project's big milestones and put them into this plan. Define the corresponding tasks in a SMART way (this includes time issues, responsibilities, exact task descriptions, description of their result). Discuss whether you need to adapt this template for your individual needs (maybe more columns to describe a task?) | Milestones and tasks are put into this schedule. | 2015-04-15 | 4 | Team | x | x | x | x
(S2) | Revise Project Plan | Revise your project plan. Make an appointment with your advisors to discuss it. Adapt tasks and milestones if reasonable. | Meeting with advisors. Improved schedule. | 2015-04-20 | 2 | Team | x | x | x | x
(M) | Literature, Brain storming Poster and Booth | Find suitable lit, ideas for poster and booth | Ideas for the poster and booth. Interesting literature (exchange lit), What is robust optimization? Why is it difficult? | 2015-04-22 | 1 | Team | x | x | x | x
(M) | Finished First Implementation | Multiple Shooting Method, without robustness, derivate some parameter (which?), simulation, visualisation (plot), assignments are listed in Protokol15042015 | Implemented & tested Naive car model with good documentation. Solved numerically the BVP with Multiple shooting | 2015-05-11 | 1 | Team | x | x | x | x
(S) | Naive Car Model | see Protokol15042015 | Naiv Model of a car | 2015-04-17 | 10 | J |  |  |  | x
(S) | Implementation Multiple Shooting Method |  | Implemented Multiple Shooting Method with tests. | 2015-04-17 | 3 | S |  | x
(S3) | Optimization Problem | Formulate Problem, How to find good starting values? Has the problem a solution? | How to choose good starting values. | 2015-04-17 | 12 | A | x |  |  | x
(S2) | Visualization of Poject Plan | Teamwork | Visualized Project Plan | 2015-04-20 | 1 | J | x | x | x | x
(S2) | Set up GitHub |  |  | 2015-05-01 | 3 | C |  |  | x
(S3) | GitHub | What is GitHub? How to use it? | We are now able to upload, download and commit files | 2015-05-04 | 1 | Team | x | x | x | x
(S) | Print the Gantt Chart | Revise your project plan. Make an appointment with your advisors to discuss it. Adapt tasks and milestones if reasonable. | Printed chart. | 2015-04-21 | 1 | J |  |  |  | x
(S1) | Present your schedule | Discuss which parts you may present in detail to your fellow students. Discuss whether there are issues you would like to collect some more feedback. | Plan for schedule presentation. | 2015-04-22 | 1 | Team | x | x | x | x
(S1) | Appointment: Modelling of Car and Modelling of Optimization Problem | Exchange knowledge of the car modelling and the math/the optimization problem in order to being able to formulate the optimization problem with the preliminary car model. | Model of car and formulation of the optimization problem. | 2015-04-24 | 1 | A, J | x |  |  | x
(S1) | Appointment: Exchange between Modelling and Implementation | Exchange knowledge, provide the formulated optimization problem for implementing. | Optimization problem is ready for being implemented. | 2015-05-06 | 1 | A, S | x | x |  | x
(S1) | Decision Extension Car Model | Which parameters should beincluded? Which parameters are uncertain? | Decision about an extended Car Model | 2015-05-11 | 1 | Team | x | x | x | x
(S2) | Robust Optimizaton - An adapted Optimizaton | How to formulate a robust optimization problem in view of [Diehl]? Problems? How can it be solved effizently at the computer? Which parameters are uncertain? | Robust Optimization Problem Formulation ready for implementation | 2015-05-11 |  | A |  |  | x
(S) | Extentend Model of Car |  | Extended Model of Car | 2015-05-11 | 14 | J |  |  |  | x
(S3) | Adapt Optimization | Robust optimal control problem, bilevel optimization, worst case formulation, linearization of the uncertainty set. | Adapted Optimization Model | 2015-05-11 | 7 | A | x
(S) | Get to Know a Program for Visualization | Which program? | name of the program and first steps. | 2015-05-18 |  | C |  |  | x
(M) | Midterm Presenation |  | Presenting the status quo. | 2015-05-27 | 1 | Team | x | x | x | x
(S1) | Create Slides | Everyone creates slides for his topic and prepares the talk | First Draft of Slides | 2015-05-22 | 3 | Team | x | x | x | x
(S2) | Prepare Presentation | Prepare presetation together. N.B. the shifts between individual talks | Perpared Presentation | 2015-05-27 |  | Team | x | x | x | x
(S1) | Design Midterm Presentation | Discuss how to present our recent project (extended car model) and prepare the presentation. | Midterm presentation ready. | 2015-05-22 | 3 | J |  |  |  | x
(M) | Poster Presentation |  | Successful presenation of your poster at TUMMS. | 2015-05-29 | 1 | Team | x | x | x | x
(S1) | Brain Storming Poster | Collect ideas how to visualize our project for pupils. | Idea how to design the poster. | 2015-04-20 | 2 | Team | x | x | x | x
(S2) | Get to Know the Visualisation Program |  |  | 2015-04-21 | 3 | C |  |  | x
(S2) | Poster Design | Design the poster with the already made sketch. | Preliminary version of the poster. | 2015-04-22 | 5 | S, A, C | x | x | x | x
(S) | First Poster Draft |  | First Poster Draft due to 29.04.2015 | 2015-04-25 | 4 | Team | x | x | x | x
(S) | Revice Poster Design and Contents |  | Final version of the poster. | 2015-04-29 | 11 | Team | x | x | x | x
(S) | Booth | How to visualize our project apart from the poster (video of the car,...) and what else we want to have in our booth (sweets, games, ...). | Fixed idea of the booth. | 2015-04-29 | 1 | Team | x | x | x | x
(S1) | Internal Poster Presentation |  | Internal Poster presenation 4.5.2015 | 2015-05-04 | 1 | Team | x | x | x | x
(S) | Poster and Exhibition Booth |  | Poster sent to advisors for printing. Concept and material for booth ready. | 2015-05-10 | 1 | S, C
(S) | Finished Booth |  | Concept for booth ready. | 2015-05-10 | 1 | A | x | x | x | x
(S) | Final Poster Hand-In |  | Hand in poster for final print. | 2015-05-11 | 1 | S, C |  |  | x
(M) | Extended Model of Car 1 | Expand our recent car model by first choosing an extended model of the car and the street, then adapting the optimization problem and using better optimization methods. After that, adjust the implementation and the simulation. In the end, testing of the overall model. | Extended Model of Car | 2015-06-01 | 1
(S) | Robust Optimization Formulation |  |  | 2015-05-11 | 14 | A | x
(S) | Visualization |  |  | 2015-05-27 | 12 | C |  |  | x
(S) | Extended Model of Car | Find an interesting model which is easy to understand and describes reality "well" | Extended Model of Car with plausibility check | 2015-05-11 | 14 | J |  |  |  | x
(S) | Implementation of Dynamics | Effizient implementation of the "extended" dynamics. | Implementated Dynamics; Derivates included; | 2015-05-24 | 7 | J |  |  |  | x
(S) | Implementation of Street Constraints |  |  | 2015-05-24 | 7 | A | x
(S) | Implementation of robust formulation |  |  | 2015-05-24 | 7 | A | x
(S1) | Derivative of Dynamics | Use Mathematica to derive the derivatives and implement |  | 2015-05-24 | 4 | J |  |  |  | x
(S) | Simulations |  |  | 2015-06-01 |  | S |  | x
(S) | Implementation of Multiple Shooting Method |  |  | 2015-05-18 | 7 | S |  | x
(M) | Extended Model of Car 2 | Expand our recent car model by first choosing an extended model of the car and the street, then adapting the optimization problem and using better optimization methods. After that, adjust the implementation and the simulation. In the end, testing of the overall model. | Extended Model of Car | 2015-06-17 | 1 |  | x | x | x | x
(S) | Extend Model of Car |  | Extended Model of Car: 3D streets | 2015-06-01 | 7 | J |  |  |  | x
(S) | Extend Optimization Problem | Are there better/faster ways, what can we improve? | Extended Optimization Problem | 2015-06-01 | 7 | A | x
(S) | Implement Changes in Opt. Problem |  | Implemented Changes | 2015-06-08 | 4 | A | x
(S) | Implementation of Dynamics |  | Implementated Dynamics; Derivates included; | 2015-06-08 | 7 |  |  |  |  | x
(S1) | Derivative of Dynamics | Use Mathematica to derive the derivatives and implement |  | 2015-05-24 | 4 |  |  |  |  | x
(S) | Implementation of Street Constraints | [5 empty] | x
(S) | Simulations |  |  | 2015-06-03 | 14 | S |  | x
(S) | Visualization |  |  | 2015-06-10 | 7 | C |  |  | x
(M) | Final Workshop |  | Presentation of your project's results. | 2015-07-11 | 1 |  | x | x | x | x
(S3) | Book Writing Center Appointment | Book appointment for 24.06 and 26.06 | Booked Appointment | 2015-05-17 | 1 | S |  | x
(S3) | Writing Abstract | How to write an Abstract? Parts of an Abstract: Motivation (Why do we care about the problem and the results? Why is it interesting? Importance, Difficulty), Problem statement (What problem?, Which scope?), Approach (Simulation, Analytic Models, ...), Results (Answer?), Concludion (Is there a win?) |  | 2015-06-20 | 7 | Team | x | x | x | x
(S3) | Writing Center Appointment |  | Reviced Abstract | 2015-06-24 | 1 | J |  |  |  | x
(S3) | Writing Center Appointment |  | Finished Abstract | 2015-06-26 | 1 | J |  |  |  | x
(S) | Talk about Final Presentation |  | Responceable person, contents | 2015-06-28 | 1 | Team | x | x | x | x
(S1) | Prepare Presentation | Prepare Presentation | First Draft of Final Presentation | 2015-06-28 | 9 | J, A | x | x | x | x
(S2) | Finalize Project | Finish Documentaton of Code and Visualization |  | 2015-06-28 | 1 | S |  | x | x
(S2) | Abstract |  | Hand in abstract by June 28th. | 2015-06-28 | 1 | Team |  |  |  | x
(S) | Final Rehearsal | Practice Final Presentation | Final Draft of Final Presentation | 2015-07-08 | 1 | Team | x | x | x | x

## Gantt Chart
Gantt Chart
|  |  |  | Hidden Milestone | KW 16 | [6 empty] | KW 17 | [6 empty] | KW 18 | [6 empty] | KW 19 | [6 empty] | KW 20 | [6 empty] | KW 21 | [6 empty] | KW 22 | [6 empty] | KW 23 | [6 empty] | KW 24 | [6 empty] | KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 | [6 empty] | KW 28 | [6 empty] | KW 29
[5 empty] | 2015-04-13 | [6 empty] | 2015-04-20 | [6 empty] | 2015-04-27 | [6 empty] | 2015-05-04 | [6 empty] | 2015-05-11 | [6 empty] | 2015-05-18 | [6 empty] | 2015-05-25 | [6 empty] | 2015-06-01 | [6 empty] | 2015-06-08 | [6 empty] | 2015-06-15 | [6 empty] | 2015-06-22 | [6 empty] | 2015-06-29 | [6 empty] | 2015-07-06 | [6 empty] | 2015-07-13
[5 empty] | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S
hidden date | time axis 2015-04-13 to 2015-07-19
Name | #VALUE! | #VALUE! | Responsible
Project Schedule | 2015-04-22 | 2015-04-22 | Team | 2015-04-22
Define Milestones & Packages | 2015-04-15 | 2015-04-18 | Team
Revise Project Plan | 2015-04-20 | 2015-04-21 | Team
Literature, Brain storming Poster and Booth | 2015-04-22 | 2015-04-22 | Team | 2015-04-22
Finished First Implementation | 2015-05-11 | 2015-05-11 | Team | 2015-05-11
Naive Car Model | 2015-04-17 | 2015-04-26 | J
Implementation Multiple Shooting Method | 2015-04-17 | 2015-04-19 | S
Optimization Problem | 2015-04-17 | 2015-04-28 | A
Visualization of Poject Plan | 2015-04-20 | 2015-04-20 | J
Set up GitHub | 2015-05-01 | 2015-05-03 | C
GitHub | 2015-05-04 | 2015-05-04 | Team
Print the Gantt Chart | 2015-04-21 | 2015-04-21 | J
Present your schedule | 2015-04-22 | 2015-04-22 | Team
Appointment: Modelling of Car and Modelling of Optimization Problem | 2015-04-24 | 2015-04-24 | A, J
Appointment: Exchange between Modelling and Implementation | 2015-05-06 | 2015-05-06 | A, S
Decision Extension Car Model | 2015-05-11 | 2015-05-11 | Team
Robust Optimizaton - An adapted Optimizaton | 2015-05-11 | 2015-05-10 | A
Extentend Model of Car | 2015-05-11 | 2015-05-24 | J
Adapt Optimization | 2015-05-11 | 2015-05-17 | A
Get to Know a Program for Visualization | 2015-05-18 | 2015-05-17 | C | 2015-05-18
Midterm Presenation | 2015-05-27 | 2015-05-27 | Team
Create Slides | 2015-05-22 | 2015-05-24 | Team
Prepare Presentation | 2015-05-27 | 2015-05-26 | Team
Design Midterm Presentation | 2015-05-22 | 2015-05-24 | J | 2015-05-22
Poster Presentation | 2015-05-29 | 2015-05-29 | Team
Brain Storming Poster | 2015-04-20 | 2015-04-21 | Team
Get to Know the Visualisation Program | 2015-04-21 | 2015-04-23 | C
Poster Design | 2015-04-22 | 2015-04-26 | S, A, C
First Poster Draft | 2015-04-25 | 2015-04-28 | Team
Revice Poster Design and Contents | 2015-04-29 | 2015-05-09 | Team
Booth | 2015-04-29 | 2015-04-29 | Team
Internal Poster Presentation | 2015-05-04 | 2015-05-04 | Team
Poster and Exhibition Booth | 2015-05-10 | 2015-05-10 | S, C
Finished Booth | 2015-05-10 | 2015-05-10 | A
Final Poster Hand-In | 2015-05-11 | 2015-05-11 | S, C | 2015-05-11
Extended Model of Car 1 | 2015-06-01 | 2015-06-01
Robust Optimization Formulation | 2015-05-11 | 2015-05-24 | A
Visualization | 2015-05-27 | 2015-06-07 | C
Extended Model of Car | 2015-05-11 | 2015-05-24 | J
Implementation of Dynamics | 2015-05-24 | 2015-05-30 | J
Implementation of Street Constraints | 2015-05-24 | 2015-05-30 | A
Implementation of robust formulation | 2015-05-24 | 2015-05-30 | A
Derivative of Dynamics | 2015-05-24 | 2015-05-27 | J | 2015-05-24
Extended Model of Car 2 | 2015-06-17 | 2015-06-17
Extend Model of Car | 2015-06-01 | 2015-06-07 | J
Extend Optimization Problem | 2015-06-01 | 2015-06-07 | A
Implement Changes in Opt. Problem | 2015-06-08 | 2015-06-11 | A
Implementation of Dynamics | 2015-06-08 | 2015-06-14
Derivative of Dynamics | 2015-05-24 | 2015-05-27
Implementation of Street Constraints
Simulations | 2015-06-03 | 2015-06-16 | S
Visualization | 2015-06-10 | 2015-06-16 | C | 2015-06-10
Final Workshop | 2015-07-11 | 2015-07-11
Book Writing Center Appointment | 2015-05-17 | 2015-05-17 | S
Writing Abstract | 2015-06-20 | 2015-06-26 | Team
Writing Center Appointment | 2015-06-24 | 2015-06-24 | J
Writing Center Appointment | 2015-06-26 | 2015-06-26 | J
Talk about Final Presentation | 2015-06-28 | 2015-06-28 | Team
Prepare Presentation | 2015-06-28 | 2015-07-06 | J, A
Finalize Project | 2015-06-28 | 2015-06-28 | S
Abstract | 2015-06-28 | 2015-06-28 | Team
Final Rehearsal | 2015-07-08 | 2015-07-08 | Team

## task extraction (hidden)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
other | other | other | other | other | other | other | other | other | other
Name | Name | Name | Name | Name | Name | Name | Name
Project Schedule | Project Schedule | Project Schedule | Project Schedule | Project Schedule | Project Schedule | Project Schedule | Project Schedule
Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages
Revise Project Plan | Revise Project Plan | Revise Project Plan | Revise Project Plan | Revise Project Plan | Revise Project Plan | Revise Project Plan | Revise Project Plan
Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth | Literature, Brain storming Poster and Booth
Finished First Implementation | Finished First Implementation | Finished First Implementation | Finished First Implementation | Finished First Implementation | Finished First Implementation | Finished First Implementation | Finished First Implementation
| Optimization Problem |  | Implementation Multiple Shooting Method |  | Visualization of Poject Plan | Naive Car Model | Naive Car Model
| Visualization of Poject Plan | Implementation Multiple Shooting Method | Visualization of Poject Plan |  | Set up GitHub |  | Optimization Problem
Optimization Problem | GitHub |  | GitHub |  | GitHub | Optimization Problem | Visualization of Poject Plan
Visualization of Poject Plan | Present your schedule | Visualization of Poject Plan | Present your schedule | Visualization of Poject Plan | Present your schedule | Visualization of Poject Plan | GitHub
| Appointment: Modelling of Car and Modelling of Optimization Problem |  | Appointment: Exchange between Modelling and Implementation | Set up GitHub | Decision Extension Car Model |  | Print the Gantt Chart
GitHub | Appointment: Exchange between Modelling and Implementation | GitHub | Decision Extension Car Model | GitHub | Robust Optimizaton - An adapted Optimizaton | GitHub | Present your schedule
| Decision Extension Car Model |  | Midterm Presenation |  | Get to Know a Program for Visualization | Print the Gantt Chart | Appointment: Modelling of Car and Modelling of Optimization Problem
Present your schedule | Adapt Optimization | Present your schedule | Create Slides | Present your schedule | Midterm Presenation | Present your schedule | Appointment: Exchange between Modelling and Implementation
Appointment: Modelling of Car and Modelling of Optimization Problem | Midterm Presenation |  | Prepare Presentation |  | Create Slides | Appointment: Modelling of Car and Modelling of Optimization Problem | Decision Extension Car Model
Appointment: Exchange between Modelling and Implementation | Create Slides | Appointment: Exchange between Modelling and Implementation | Poster Presentation |  | Prepare Presentation | Appointment: Exchange between Modelling and Implementation | Extentend Model of Car
Decision Extension Car Model | Prepare Presentation | Decision Extension Car Model | Brain Storming Poster | Decision Extension Car Model | Poster Presentation | Decision Extension Car Model | Midterm Presenation
| Poster Presentation |  | Poster Design | Robust Optimizaton - An adapted Optimizaton | Brain Storming Poster |  | Create Slides
| Brain Storming Poster |  | First Poster Draft |  | Get to Know the Visualisation Program | Extentend Model of Car | Prepare Presentation
Adapt Optimization | Poster Design |  | Revice Poster Design and Contents |  | Poster Design |  | Design Midterm Presentation
| First Poster Draft |  | Booth | Get to Know a Program for Visualization | First Poster Draft |  | Poster Presentation
Midterm Presenation | Revice Poster Design and Contents | Midterm Presenation | Internal Poster Presentation | Midterm Presenation | Revice Poster Design and Contents | Midterm Presenation | Brain Storming Poster
Create Slides | Booth | Create Slides | Finished Booth | Create Slides | Booth | Create Slides | Poster Design
Prepare Presentation | Internal Poster Presentation | Prepare Presentation | Extended Model of Car 2 | Prepare Presentation | Internal Poster Presentation | Prepare Presentation | First Poster Draft
| Finished Booth |  | Simulations |  | Finished Booth | Design Midterm Presentation | Revice Poster Design and Contents
Poster Presentation | Robust Optimization Formulation | Poster Presentation | Final Workshop | Poster Presentation | Final Poster Hand-In | Poster Presentation | Booth
Brain Storming Poster | Implementation of Street Constraints | Brain Storming Poster | Book Writing Center Appointment | Brain Storming Poster | Visualization | Brain Storming Poster | Internal Poster Presentation
| Implementation of robust formulation |  | Writing Abstract | Get to Know the Visualisation Program | Extended Model of Car 2 |  | Finished Booth
Poster Design | Extended Model of Car 2 | Poster Design | Talk about Final Presentation | Poster Design | Visualization | Poster Design | Extended Model of Car
First Poster Draft | Extend Optimization Problem | First Poster Draft | Prepare Presentation | First Poster Draft | Final Workshop | First Poster Draft | Implementation of Dynamics
Revice Poster Design and Contents | Implement Changes in Opt. Problem | Revice Poster Design and Contents | Finalize Project | Revice Poster Design and Contents | Writing Abstract | Revice Poster Design and Contents | Derivative of Dynamics
Booth | Implementation of Street Constraints | Booth | Final Rehearsal | Booth | Talk about Final Presentation | Booth | Extended Model of Car 2
Internal Poster Presentation | Final Workshop | Internal Poster Presentation |  | Internal Poster Presentation | Prepare Presentation | Internal Poster Presentation | Extend Model of Car
| Writing Abstract |  |  |  | Finalize Project |  | Implementation of Dynamics
Finished Booth | Talk about Final Presentation | Finished Booth |  | Finished Booth | Final Rehearsal | Finished Booth | Derivative of Dynamics
| Prepare Presentation |  |  | Final Poster Hand-In |  |  | Final Workshop
| Final Rehearsal | [5 empty] | Writing Abstract
Robust Optimization Formulation | [6 empty] | Writing Center Appointment
|  |  |  | Visualization |  |  | Writing Center Appointment
[6 empty] | Extended Model of Car | Talk about Final Presentation
[6 empty] | Implementation of Dynamics | Prepare Presentation
Implementation of Street Constraints | [6 empty] | Abstract
Implementation of robust formulation | [6 empty] | Final Rehearsal
Derivative of Dynamics
Extended Model of Car 2 |  | Extended Model of Car 2 |  | Extended Model of Car 2 |  | Extended Model of Car 2
Extend Model of Car
Extend Optimization Problem
Implement Changes in Opt. Problem
Implementation of Dynamics
Derivative of Dynamics
Implementation of Street Constraints
Simulations
Visualization
Final Workshop |  | Final Workshop |  | Final Workshop |  | Final Workshop
Book Writing Center Appointment
Writing Abstract |  | Writing Abstract |  | Writing Abstract |  | Writing Abstract
Writing Center Appointment
Writing Center Appointment
Talk about Final Presentation |  | Talk about Final Presentation |  | Talk about Final Presentation |  | Talk about Final Presentation
Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation
|  | Finalize Project |  | Finalize Project
Abstract
Final Rehearsal |  | Final Rehearsal |  | Final Rehearsal |  | Final Rehearsal

## Time Sheet A
Workload
Task | Time Spent (hours) | When | Notes | Total Hours: | 60.25
Meeting with Advisor | 1.5 | 15.04.2015 | siehe Protokoll
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Skype Conference | 2 | 17.04.215 | siehe Protokoll
Working on Papers (Gerdts, Diehl) | 2 | 18.4.2015, 19.4.2015, 20.4.2015
Protokolle | 1 | 18.4.2015, 22.4.2015
Skype Conference | 1 | 20.04.2015 | siehe Protokoll
Project Schedule | 1 | 20.04.2015, 21.04.2015
Meeting with Advisor | 1.5 | 22.04.2015 | siehe Protokoll
Working on the carmodel and how to formulate the optimization problem | 2 | 23.4.2015
Meeting with Johannes | 2.5 | 24.4.2015 | Posterentwurf (Kästen und Überschrift) und Formulierung des Optimierungsproblems
Posterdesign | 0.5 | 24.4.2015
Multiple shooting, Runge Kutta und weitere Grundlagen | 1 | 24.4.2015
Diskretisierung Optimierungsproblem | 3 | 26.4.2015, 27.4.2015
Posterdesign Treffen | 1.75 | 27.4.2015 | siehe Protokoll
Automodell überarbeitet, Protokoll | 0.5 | 27.4.2015
Posterdesign | 0.5 | 27.04.2015 | Kästen überarbeitet
Diskretisierung Optimierungsproblem | 1 | 30.04.2015, 31.04.2015 | Ergebnisse geTEXt
Treffen | 1.5 | 29.04.2015 | Poster und Diskretisierung Optimierungsproblem
Treffen mit Advisor | 1.5 | 29.04.2015 | Poster und Diskretisierung Optimierungsproblem
GitHub | 1 | 03.05.2015 | Skypen mit Christian, Account, Platform kennenlernen
Gedanken über mögliche Parameter | 0.5 | 03.05.2015
Formulierung Optimierungsproblem mit Parametern | 2.5 | 03.05.2015 | Paper von Diehl, Übertrag auf unser Problem
Code zur ersten Implementierung angeschaut | 0.5 | 03.05.2015
Github Treffen | 1 | 04.05.2015
Boothkonzept ausgearbeitet | 3 | 04.05.2015, 06.05.2015, 07.05.2015 | Konzept und Organisation
Meeting with Advisor | 2.5 | 06.05.2015 | Booth, Poster und Paper von Diehl
Treffen wegen der Parameter | 2 | 11.05.2015 | bisherige Implementierung, Parameter
Parameter | 2 | 11.052015, 12.5.2015 | Protokoll, Recherche
Treffen mit Advisor | 1.5 | 13.05.2015 | siehe Protokoll
Slackformulierung unseres Optimalsteuerungsproblems | 1.5 | 14.05.2015 | Formulierung unseres robusten Optimalsteuerungsproblems mit Slackvariablen nach Diehl
Treffen | 2 | 18.05.2015 | siehe Protokoll
Formulierung unseres robusten Optimalsteuerungsproblems | 1.5 | 19.05.2015, 20.05.2015 | Rückformulierung der Slackformulierung in Standardform, neue Zielfunktion ohne Integral, Nebenbedingungen mit t_{i} anstatt T
Automodell verifiziert | 0.5 | 19.05.2015
Midterm Presentation | 0.5 | 20.05.2015 | Gliederung und Inhalt meines Teils überlegen
Treffen mit Sebastian | 1 | 21.05.2015 | Formulierung des Optimalsteuerungsproblems, Präsentation
Midterm Presentation | 6 | 22.05., 24.05, 25.05.2015 | Vorbereitung/Erstellung des Vortrages
Midterm Presentation | 1.5 | 2015-05-26 | Fertigstellen (Üben) des Vortrages
Formulierung unseres robusten Optimalsteuerungsproblems | 1.5 | 2015-05-25

## Time Sheet C
Workload
Task | Time Spent (hours) | When | Notes | Total Hours: | 58
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Get to Know a Program for Visualization | 2 | 19.4.2015, 20.4.2015 | Some tutorials for blender (designing landscapes and steets) and found a nice model of a car
Skype Konferenz | 0.75 | 20.04.2015
Work through texturing in blender | 2 | 21.04.2015
Weekly meeting | 4 | 22.04.2015
Poster Design | 3 | 23.04.2015 | Einarbeitung (Inkscape), Schilder/Fahrbahnmarkierungen (test)
Poster Design | 3 | 24.04.2015 | Autos/Straße/Fahrbahnmarkierungen
Project Schedule | 1
Poster evaluation | 1 | 26.04.2015 | Prüfung auf verständlichkeit durch Fachfremde
Poster Design meeting | 1.75 | 27.04.2015
Poster Design | 2 | 27.04.2015 | Rearrangement, Grafiken ausgetauscht, Straße verbessert
Weekly meeting | 3 | 29.04.2015
Poster Design | 3 | 29.04.2015 | Feintuning, Umgestaltung
Github management und support | 2.5 | 01.05.2015, 03.05.2015
Generierung von Straßen in Blender | 2 | 03.05.2015
Github meeting | 1 | 04.05.2015
Poster Design | 4 | 06.05.2015 | Änderungen für den Finalentwurf
Meeting with advisor | 3 | 06.05.2015
Poster Finnishing | 1 | 07.05.2015
Parameter Meeting | 2 | 11.05.2015
Team meeting | 2 | 18.05.2015
Team meeting | 1 | 20.05.2015
Blender Texturen | 5 | 19.05.2015 | Straße sieht wie eine Straße aus, Wiese, Lichtquellen hinzugefügt
Blender Animation | 3 | 20.05.2015 | erstes animiertes Video
Blender Verbessertes Automodell | 3 | 21.05.2015 | Die Texturen werden nicht richtig übernommen => Scheiben undurchsichtig, Lack matt, keine Rücklichter...

## Time Sheet J
Workload
Task | Time Spent (hours) | When | Notes | Total Hours: | 57.75
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 3 | 17.04.2015, 18.04.2015
Skype Conference | 1.75 | 17.04.215
Runge-Kutta method | 0.5 | 2015-04-17
Durchstöbern von Gerdts Internetseiten | 0.5 | 2015-04-18
Skype Conference | 1 | 2015-04-20
Finish Project Schedule | 0.75 | 2015-04-21
Project Schedule | 2 | 2015-04-22
Lecture | 1.5 | 2015-04-22
Meeting with Advisor | 1.5 | 2015-04-22
Meeting with Johannes | 2.5 | 24.4.2015 | Posterentwurf ,Formulierung des Optimierungsproblems
Robust Optimization | 1 | 2015-04-25 | Ben-Tal
Poster Presentation | 0.5 | 2015-04-25 | DIN Schriften
Fertigstellung: First Car Model | 0.5 | 2015-04-26 | bsfc Interpolation
Lecture | 1.5 | 27.04.2015
Poster Design | 1.5 | 27.04.2015
Lecture | 1.5 | 29.04.2015
Team Besprechung | 1.5 |  | Nächsten Schritte, Schnittstellenklärung
Bestimmung zulässiger Startpunkte | 0.5 | 7.5.15 | Welche Verfahren gibt es? Welche Möglichkeiten (bzw Vorschläge bietet) mathworks
Symbolisches Differenziern mit Maple | 2.5 |  | mühsellige Eingabe
GitHub | 2
Code bzw Car Model debuggen | 4 | 9.5.15 | Fehler in Modellierung (maximale Beschleundigungsfähigkeit, mein Fehler)
Presentation | 0.5 |  | Brain Storming
GitHub Treffen | 1
Treffen mit Betreuer | 3 | 6.5.15 | Poster, Booth, Diehl
Treffen mit Team | 2 | 11.05.15 | Wie sieht unser robustes Optimierungsproblem aus? Welche Parameter betrachten wir als "unsicher"
Haftreibung | 2.5 | 12.05. | Haftreibung in Abhängigkeit von Wetter wobei Wetter(t) \in [0,1]. Problem: Wie bestimmen wir den Kraftschluss
Treffen mit Betreuer | 1.5 | 13.05
Treffen mit Team | 2 | 18.05 | siehe Protokol
Automodell | 4 | 16- 18.05.2015 | Literaturrechere: Was ist eine sinnvolle Modellierung? Sinnvoll heißt dabei möglichst einfach allerdings möglichs realitätsnah.
Midterm Presentation | 0.5 | 20.05.2015 | Erstellung der Latex- Präsentation; Welche Inhalte stelle ich vor? Wie stelle ich diese vor?
Treffen mit Team | 1 | 20.05.2015 | siehe Protokol
Treffen mit Sebastian | 0.75 | 21.05.2015 | Automodell besprochen
Präsentation | 2 | 23.05.2015 | Meinen Foliensatz erstellt, Anmerkungen zu anderen Sätzen erstellt
Präsentation überarbeitet | 3 | 2015-05-26 | Anmerkungen zur Endterm: Entweder ich allein übernehme die Erstellung oder wir sprechen Layout und ähnliches genauer ab. Probleme bei aufgeteilter Erstellung: Gesamtbild ist unschön; Sollten wir derart viele Boxen verwenden, dann nur Umrahmung -> Template erstellen.
Robustes Automodell | 1 | 2015-05-25 | Bereit um Ableitungen zu bestimmen

## Time Sheet S
Workload
Task | Time Spent (hours) | When | Notes | Total Hours: | 53
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1
Present your schedule
Skype Conference | 2 | 17.04.15
Weekly Meeting | 4 | 22.4.15
Multiple Shooting theory and implementation in Matlab | 2 | 20.4.15
Poster Design | 6 | 23.4.15
Meeting for Poster | 1.5 | 27.4.15
Poster Update | 0.5 | 27.4.15
Modell Besprechung im Team und mit Sebastian | 3 | 29.4.15
Poster Update | 1 | 29.4.15
1. Implementation | 12 | 2.5.-4.5.
Github Treffen | 1 | 4.5.
Montags Treffen | 2 | 11.5.
Code Update | 1 | 11.5.
Mittwoch Treffen | 2 | 13.05.
Testen von Luftwiderstand und Reibung im Code | 1 | 14.05.
Montag Treffen | 2 | 18.05.
Testen von Luftwiderstand und Reibung im Code | 2 | 19.05.
Treffen Besprechung des Vortrags und Modell | 1 | 20.5.
Parameter c_1 und c_2 Testen, Plots für Präsentation erstellen | 1 | 20.5.
Präsentation erstellen | 3 | 22.5.
Präsentation überarbeiten | 2 | 26.5.

## Time Sheet TM5
Workload
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
other | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1

## temporary
Temporary Sheet for Plan Development
Milestones & Workpackages
Typ | Name | Description | Result | Start | Duration (days) | Responsible | Annkathrin | Sabina | Christian | Johannes
(M) | Project Schedule | Develop a project schedule for the whole project. This contains all milestones and the corresponding subtasks in a SMART way. |  | 2015-04-22 | 1 | Team | x | x | x | x
(S) | Define Milestones & Packages | Define the project's big milestones and put them into this plan. Define the corresponding tasks in a SMART way (this includes time issues, responsibilities, exact task descriptions, description of their result). Discuss whether you need to adapt this template for your individual needs (maybe more columns to describe a task?) | Milestones and tasks are put into this schedule. | 2015-04-15 | 4 | Team | x | x | x | x
(S2) | Revise Project Plan | Revise your project plan. Make an appointment with your advisors to discuss it. Adapt tasks and milestones if reasonable. | Meeting with advisors. Improved schedule. | 2015-04-20 | 2 | Team | x | x | x | x
(M) | Literature, Brain storming Poster and Booth | Find suitable lit, ideas for poster and booth | Ideas for the poster and booth. Interesting literature (exchange lit), What is robust optimization? Why is it difficult? | 2015-04-22 | 1 | Team | x | x | x | x
(M) | Finished First Implementation | Multiple Shooting Method, without robustness, derivate some parameter (which?), simulation, visualisation (plot), assignments are listed in Protokol15042015 | Implemented & tested Naive car model with good documentation. Solved numerically the BVP with Multiple shooting | 2015-05-11 | 1 | Team | x | x | x | x
(S) | Naive Car Model | see Protokol15042015 | Naiv Model of a car | 2015-04-17 | 10 | J |  |  |  | x
(S) | Implementation Multiple Shooting Method |  | Implemented Multiple Shooting Method with tests. | 2015-04-17 | 3 | S |  | x
(S3) | Optimization Problem | Formulate Problem, How to find good starting values? Has the problem a solution? | How to choose good starting values. | 2015-04-17 | 12 | A | x |  |  | x
(S2) | Visualization of Poject Plan | Teamwork | Visualized Project Plan | 2015-04-20 | 1 | J | x | x | x | x
(S2) | Set up GitHub |  |  | 2015-05-01 | 3 | C |  |  | x
(S3) | GitHub | What is GitHub? How to use it? | We are now able to upload, download and commit files | 2015-05-04 | 1 | Team | x | x | x | x
(S) | Print the Gantt Chart | Revise your project plan. Make an appointment with your advisors to discuss it. Adapt tasks and milestones if reasonable. | Printed chart. | 2015-04-21 | 1 | J |  |  |  | x
(S1) | Present your schedule | Discuss which parts you may present in detail to your fellow students. Discuss whether there are issues you would like to collect some more feedback. | Plan for schedule presentation. | 2015-04-22 | 1 | Team | x | x | x | x
(S1) | Appointment: Modelling of Car and Modelling of Optimization Problem | Exchange knowledge of the car modelling and the math/the optimization problem in order to being able to formulate the optimization problem with the preliminary car model. | Model of car and formulation of the optimization problem. | 2015-04-24 | 1 | A, J | x |  |  | x
(S1) | Appointment: Exchange between Modelling and Implementation | Exchange knowledge, provide the formulated optimization problem for implementing. | Optimization problem is ready for being implemented. | 2015-05-06 | 1 | A, S | x | x |  | x
(S1) | Decision Extension Car Model | Which parameters should beincluded? Which parameters are uncertain? | Decision about an extended Car Model | 2015-05-11 | 1 | Team | x | x | x | x
(S2) | Robust Optimizaton - An adapted Optimizaton | How to formulate a robust optimization problem in view of [Diehl]? Problems? How can it be solved effizently at the computer? Which parameters are uncertain? | Robust Optimization Problem Formulation ready for implementation | 2015-05-11 |  | A |  |  | x
(S) | Extentend Model of Car |  | Extended Model of Car | 2015-05-11 | 14 | J |  |  |  | x
(S3) | Adapt Optimization | Robust optimal control problem, bilevel optimization, worst case formulation, linearization of the uncertainty set. | Adapted Optimization Model | 2015-05-11 | 7 | A | x
(S) | Get to Know a Program for Visualization | Which program? | name of the program and first steps. | 2015-05-18 |  | C |  |  | x
(M) | Midterm Presenation |  | Presenting the status quo. | 2015-05-27 | 1 | Team | x | x | x | x
(S1) | Create Slides | Everyone creates slides for his topic and prepares the talk | First Draft of Slides | 2015-05-22 | 3 | Team | x | x | x | x
(S2) | Prepare Presentation | Prepare presetation together. N.B. the shifts between individual talks | Perpared Presentation | 2015-05-27 |  | Team | x | x | x | x
(S1) | Design Midterm Presentation | Discuss how to present our recent project (extended car model) and prepare the presentation. | Midterm presentation ready. | 2015-05-22 | 3 | J |  |  |  | x
(M) | Poster Presentation |  | Successful presenation of your poster at TUMMS. | 2015-05-29 | 1 | Team | x | x | x | x
(S1) | Brain Storming Poster | Collect ideas how to visualize our project for pupils. | Idea how to design the poster. | 2015-04-20 | 2 | Team | x | x | x | x
(S2) | Get to Know the Visualisation Program |  |  | 2015-04-21 | 3 | C |  |  | x
(S2) | Poster Design | Design the poster with the already made sketch. | Preliminary version of the poster. | 2015-04-22 | 5 | S, A, C | x | x | x | x
(S) | First Poster Draft |  | First Poster Draft due to 29.04.2015 | 2015-04-25 | 4 | Team | x | x | x | x
(S) | Revice Poster Design and Contents |  | Final version of the poster. | 2015-04-29 | 11 | Team | x | x | x | x
(S) | Booth | How to visualize our project apart from the poster (video of the car,...) and what else we want to have in our booth (sweets, games, ...). | Fixed idea of the booth. | 2015-04-29 | 1 | Team | x | x | x | x
(S1) | Internal Poster Presentation |  | Internal Poster presenation 4.5.2015 | 2015-05-04 | 1 | Team | x | x | x | x
(S) | Poster and Exhibition Booth |  | Poster sent to advisors for printing. Concept and material for booth ready. | 2015-05-10 | 1 | S, C
(S) | Finished Booth |  | Concept for booth ready. | 2015-05-10 | 1 | A | x | x | x | x
(S) | Final Poster Hand-In |  | Hand in poster for final print. | 2015-05-11 | 1 | S, C |  |  | x
(M) | Extended Model of Car 1 | Expand our recent car model by first choosing an extended model of the car and the street, then adapting the optimization problem and using better optimization methods. After that, adjust the implementation and the simulation. In the end, testing of the overall model. | Extended Model of Car | 2015-06-01 | 1
(S) | Robust Optimization Formulation |  |  | 2015-05-11 | 14 | A | x
(S) | Visualization |  |  | 2015-05-27 | 12 | C |  |  | x
(S) | Extended Model of Car | Find an interesting model which is easy to understand and describes reality "well" | Extended Model of Car with plausibility check | 2015-05-11 | 14 | J |  |  |  | x
(S) | Implementation of Dynamics | Effizient implementation of the "extended" dynamics. | Implementated Dynamics; Derivates included; | 2015-05-24 | 7 | J |  |  |  | x
(S) | Implementation of Street Constraints |  |  | 2015-05-24 | 7 | A | x
(S) | Implementation of robust formulation |  |  | 2015-05-24 | 7 | A | x
(S1) | Derivative of Dynamics | Use Mathematica to derive the derivatives and implement |  | 2015-05-24 | 4 | J |  |  |  | x
(S) | Simulations |  |  | 2015-06-01 |  | S |  | x
(S) | Implementation of Multiple Shooting Method |  |  | 2015-05-18 | 7 | S |  | x
(M) | Extended Model of Car 2 | Expand our recent car model by first choosing an extended model of the car and the street, then adapting the optimization problem and using better optimization methods. After that, adjust the implementation and the simulation. In the end, testing of the overall model. | Extended Model of Car | 2015-06-17 | 1 |  | x | x | x | x
(S) | Extend Model of Car |  | Extended Model of Car: 3D streets | 2015-06-01 | 7 | J |  |  |  | x
(S) | Extend Optimization Problem | Are there better/faster ways, what can we improve? | Extended Optimization Problem | 2015-06-01 | 7 | A | x
(S) | Implement Changes in Opt. Problem |  | Implemented Changes | 2015-06-08 | 4 | A | x
(S) | Implementation of Dynamics |  | Implementated Dynamics; Derivates included; | 2015-06-08 | 7 |  |  |  |  | x
(S1) | Derivative of Dynamics | Use Mathematica to derive the derivatives and implement |  | 2015-05-24 | 4 |  |  |  |  | x
(S) | Implementation of Street Constraints | [5 empty] | x
(S) | Simulations |  |  | 2015-06-03 | 14 | S |  | x
(S) | Visualization |  |  | 2015-06-10 | 7 | C |  |  | x
(M) | Final Workshop |  | Presentation of your project's results. | 2015-07-11 | 1 |  | x | x | x | x
(S3) | Book Writing Center Appointment | Book appointment for 24.06 and 26.06 | Booked Appointment | 2015-05-17 | 1 | S |  | x
(S3) | Writing Abstract | How to write an Abstract? Parts of an Abstract: Motivation (Why do we care about the problem and the results? Why is it interesting? Importance, Difficulty), Problem statement (What problem?, Which scope?), Approach (Simulation, Analytic Models, ...), Results (Answer?), Concludion (Is there a win?) |  | 2015-06-20 | 7 | Team | x | x | x | x
(S3) | Writing Center Appointment |  | Reviced Abstract | 2015-06-24 | 1 | J |  |  |  | x
(S3) | Writing Center Appointment |  | Finished Abstract | 2015-06-26 | 1 | J |  |  |  | x
(S) | Talk about Final Presentation |  | Responceable person, contents | 2015-06-28 | 1 | Team | x | x | x | x
(S1) | Prepare Presentation | Prepare Presentation | First Draft of Final Presentation | 2015-06-28 | 9 | J, A | x | x | x | x
(S2) | Finalize Project | Finish Documentaton of Code and Visualization |  | 2015-06-28 | 1 | S |  | x | x
(S2) | Abstract |  | Hand in abstract by June 28th. | 2015-06-28 | 1 | Team |  |  |  | x
(S) | Final Rehearsal | Practice Final Presentation | Final Draft of Final Presentation | 2015-07-08 | 1 | Team | x | x | x | x